## Implementation Status
Module | Status | Completion % | What's Working | What's Partial / Stubbed | What's Missing | Priority | Notes
Authentication | Partial | 90 | Local register/login (3 flows), email verification, password reset/change, JWT access + rotating refresh tokens with Redis sessions and DB token blacklist, logout/logout-all, OAuth (Google/GitHub/Apple) with link/unlink, invitations CRUD, one-time OAuth code exchange, set-password activation. | updateProfile() nesting bug so name/preferences-only updates save nothing; OAuth tokens stored plaintext; TokenBlacklist checked in Postgres per-request. | POST /auth/oauth/verify-2fa is broken: @Public but reads @CurrentUser (undefined) then dereferences user.id → throws. | High | JwtStrategy reads flat JWT_SECRET vs module jwt.secret; access token expiresIn default 7d contradicts advertised 900s; redundant double subscription creation on registration.
Users | Complete | 92 | Full CRUD via QueryBuilder, password lifecycle wired to Mail+events, preferences/status/last-login, search, findBy helpers, extensive bulk ops (delete, role/permission add-remove-replace, status, email, invite). Entity has bcrypt hooks + getEffectivePermissions. 20+ guarded endpoints. | getStatistics() byRole map hardcodes SUPER_ADMIN/TENANT_ADMIN/USER only, dropping CUSTOMER/CUSTOMER_USER counts; class-level AuditInterceptor commented out. | repositories/user.repository.ts is 0 bytes (unused). | High | No TODO/NotImplemented/stubs. Only gaps: empty repo file + incomplete statistics role breakdown.
Tenants | Partial | 72 | create (name/email conflict check), findAll paginated, findOne, findByName, update, soft-delete, activate, suspend, getStatistics. Entity fully modeled with TenantStatus enum; controller full CRUD + Swagger. | getUsage() is an explicit TODO mock returning hardcoded zeros; DTOs advertise byIndustry/byCountry/percentage fields the service never populates. | CreateTenantDto exposes title/description/additionalInfo/address2 with NO matching entity columns (silent data loss); findAll search references nonexistent tenant.title column → QueryFailedError when search supplied. | High | getUsage mock + DTO/entity mismatch + broken search are main issues; CRUD/status transitions solid.
Customers | Complete | 90 | Transactional create (customer + linked CUSTOMER user + set-password token + event), full paginated CRUD, status/bulk-status, search, statistics, public customers, setPasswordFromToken + resend invitation, two-tier allocated-limit validation, full CustomerListener (created/deleted/cascade/status-sync). | setPasswordFromToken has NO controller route exposing it (activation endpoint missing); remove() uses hard delete (soft-delete commented out); create() duplicate check only catches exact phone+email+tenant triple. | None (no NotImplemented/TODO/empty bodies). | High | Solid production-shaped code; main gap is un-exposed set-password route + hard-delete deviation.
Customer-users | Partial | 85 | createCustomerUser (email uniqueness, role resolution, set-password token, invite email, event), assign/remove/transfer/bulk-assign, access checks, statistics, search, role-aware getTenantHierarchy tree, getCustomerUserWithResources. Controller endpoints wired. | resendCustomerUserInvitation() emails the WRONG recipient (caller/admin instead of target) though token rotates; several routes rely on global guards without explicit @UseGuards(RolesGuard). | Public set-password activation endpoint fully commented out (lines 42-50) → CUSTOMER_USER self-activation has no exposed route. | High | Feature-complete surface with two real defects: wrong-recipient resend + commented-out activation.
Roles | Complete | 97 | Entity with tenant scoping, role_permissions M2M, users inverse M2M. Service: create, findAll (paginated w/ system/custom counts), findOne, findByName, update, remove, assign/removePermissions, getSystemRoles, getTenantRoles, getUsersCount. 10 wired endpoints. | None. | None. | Medium | No stubs. Controller lacks explicit auth decorators despite being RBAC surface — relies on global guards.
Permissions | Complete | 95 | Entity with tenant scoping, resource/action/isSystem, M2M relations. Service: create, findAll, findByResource, findOne, findByResourceAndAction, update, remove, softRemove, getUniqueResources, bulkCreate. 8 wired endpoints. | None. | None. | Medium | Unique constraint is (tenantId,resource,action) but service uniqueness checks match on (resource,action) only → cross-tenant false-conflicts possible. create() doesn't set tenantId from caller.
Two-factor | Partial | 90 | TOTP/authenticator setup (speakeasy + QR), email OTP via MailService, backup code gen/verify/regen, enable/disable, login-time verifyCode — all wired end-to-end. | SMS 2FA flow fully coded but send is a stub: sendSMSCode() logs the code with 'TODO: Integrate SMS provider (Twilio/AWS SNS)'. | No real SMS provider. Minor: methods typed userId:User (whole entity) rather than id string. | Medium | Only gap is SMS transport; authenticator + email are production-ready.
User-settings | Complete | 100 | Full CRUD: get/create-on-demand, update general/notification/display, update-all, reset-to-default, dashboard layout, widget preferences, custom preferences. Entity + controller (/settings) + DTOs consistent. | None. | No tenantId scoping (user-scoped only) — diverges from platform multi-tenant convention but acceptable for per-user prefs. | Low | Simplest module; fully functional, no TODOs/stubs.
Profiles | Complete | 95 | DeviceProfiles + AssetProfiles: CRUD, default mgmt, clone, statistics, telemetry validation, asset export/import, hierarchy/location/device/attribute schema validation, calculated fields, usage details. Two controllers with role guards. | calculateFields() uses new Function() (eval) — code self-flags as unsafe for production. Role-based query filtering has no branch for CUSTOMER/SUPER_ADMIN. | Nothing structural. | Medium | Mature; main risk is eval-based expression evaluator + a filtering-scope gap.
Subscriptions | Complete | 95 | Full plan matrix (FREE/STARTER/PROFESSIONAL/ENTERPRISE) with pricing/limits/features/trials. Create, usage stats+warnings, upgrade (payment-gated), scheduled downgrade+cancel, immediate cancel, renewal with pessimistic locking, JSONB usage increment/decrement, cron jobs, invoices + PDF generation. | cancel() creates a new FREE subscription then saves old as CANCELLED (two active-ish rows possible). Some dead commented code; unused helpers. | Nothing significant. | High | Gates access platform-wide (guards read features/limits/usage). Production-grade; minor cancel-flow smell.
Payments | Complete | 90 | Moyasar fully wired: hosted-invoice creation with validation + pending reuse, verifyPayment idempotency, transactional processSuccessfulPayment, failed-payment handling, webhook HMAC-SHA256 verification, refund via API, payment history, admin review/retry endpoints. | refundPayment has 'TODO: Handle subscription downgrade'; admin endpoints use only JwtAuthGuard with 'TODO: Add AdminGuard'; retrySubscriptionUpdate passes payment.userId where tenantId expected (probable bug). | Stripe is present-but-unwired dependency (enum + entity comments reference it, no code path). | High | Revenue-critical, solid for Moyasar. Gaps: missing AdminGuard, post-refund downgrade, tenantId/userId mix-up in admin retry, dormant Stripe.
Devices | Complete | 90 | Full device CRUD, MQTT credential gen/regen/verify, per-protocol topic strategy (generic MQTT / LoRaWAN Milesight / ChirpStack), capabilities endpoint, statistics, activate/deactivate, bulk status update (plan-gated), customer assign/unassign, codecId auto-resolution from manufacturer+model. | Auto-register path depends on SYSTEM_TENANT_ID/SYSTEM_USER_ID env, falls back to using tenantId as userId. | Nothing material. | High | Device control endpoints (command/rpc/telemetry) deliberately live in GatewayController to avoid circular dep. Production-grade.
Codecs | Complete | 95 | CodecRegistryService with codecId/manufacturer+model/canDecode auto-detect, encode/decode, capability catalog. ~95 Milesight codecs + generic MQTT-JSON codec. Sampled WS558/DS3604 fully implemented incl. bidirectional encode/decode + rich metadata. | DS3604 binary image payload (0xFB 0x02) intentionally skipped (bytes consumed, not exposed). A few codec files exist on disk but not registered in ALL_CODECS. | Non-Milesight manufacturers (catalog is Milesight-only). | High | Most complete part of the platform. Registry falls back to raw-wrap on unknown payloads rather than throwing.
Telemetry | Complete | 88 | TelemetryConsumer (Kafka telemetry.device.raw → persist → alarm check → WebSocket broadcast → forward to validated topic + rules.input). Service: create/batch, tenant-scoped query, latest, statistics, DATE_TRUNC aggregation, JSONB timeseries, CSV export, retention. Gateway (Socket.IO) + Bull processor implemented. Has unit spec. | getLatest Redis cache path fully commented out (DB every read); leftover console.log in storeTelemetry; HTTP-ingest create() bypasses Kafka so skips automations/WS. | None critical. | High | Core ingestion→storage→broadcast pipeline works end-to-end.
Protocols | Partial | 62 | DeviceListenerService (unified entry: find/auto-register, codec decode, activity update, Kafka publish). HTTPAdapter (ingestion + batch) works. ModbusAdapter fully implemented (TCP/RTU, polling, scaling, write). CoAPAdapter works (server, telemetry POST, downlink). | CoAP TODOs: pending-command queue returns empty, device IP from env only. HTTPAdapter console.log-heavy. Adapters hardcode tenantId 'default'. | BLEAdapter is a placeholder (noble import + handlers commented out; sendCommand TODO). ZigbeeAdapter is a placeholder (zigbee-herdsman Controller commented out; never runs). | High | MQTT handled by lib/mqtt. Adapters env-gated (off by default). BLE + Zigbee non-functional; HTTP/Modbus/CoAP real.
Gateway | Complete | 85 | sendCommand resolves topic+encoding per device.protocol (LoRaWAN & ChirpStack via CodecRegistry.encode; generic MQTT passthrough) and publishes via single MQTTService. sendRpcRequest, updateDeviceAttributes, publishTelemetry, verifyDeviceConnection (5-min cache), status. Controller: command/rpc/telemetry with access checks. | Generic MQTT default case still builds a milesight/downlink/{devEUI} topic (likely bug for non-LoRaWAN). verifyDeviceConnection does full findAll scan (inefficient). | None critical. | High | Thin but functional downlink layer; owns all MQTT publish to avoid duplicate clients.
Device-commands | Complete | 83 | Full command lifecycle: create (persist + publish to Kafka device.commands), status query, list by device/user, cancel, internal status updates. Consumer consumes device.commands(.retry), routes delivery via GatewayService.sendCommand, retries with exponential backoff, handles scheduled commands. | Retry + scheduling use in-process setTimeout (timers lost on restart). No dead-letter queue. Leftover console.log. | None critical. | Medium | End-to-end flow works via Kafka + Gateway; durability of scheduled/retry timers is the main gap.
Assets | Complete | 95 | Full CRUD, hierarchy tree/path/children with circular-ref prevention, device assign/unassign/bulk, location search (Haversine), statistics, customer assign/unassign, attributes update. Role/tenant/customer scoping. QueryBuilder pagination. | asset-type.entity.ts effectively empty (AssetType is an enum instead). wouldCreateCircularReference accepts a tenantId param callers never pass. | No standalone AssetType entity despite the file existing. | Medium | Production-ready CRUD + hierarchy. Empty asset-type.entity.ts is dead file, not functional gap.
Attributes | Partial | 80 | Polymorphic attribute store (string/number/boolean/json), create, saveAttributes (upsert), findByEntity/findByKeys, getLatestValues, delete single/multiple, findByCustomer, entity-access verification, denormalized customerId. Controller wired for device/asset. | getTimeseries() is an explicit stub (TODO) — returns current value as a single fake data point with Date.now() timestamp instead of real historical data. | Real time-series retrieval (should join telemetry). No historical persistence of attribute changes. | Medium | Core KV storage solid; only timeseries endpoint is faked. Would mislead any UI charting attribute history.
Edge | Complete | 95 | Full edge lifecycle: CRUD, edgeToken gen/rotation, token-auth heartbeat, metrics snapshot persistence, @Cron offline detection, metrics history, device assign/unassign with count sync, command dispatch + agent poll + ack, aggregate statistics. Agent routes @Public + edgeToken-secured. | EdgeModule re-calls ScheduleModule.forRoot()/EventEmitterModule.forRoot() locally (possible duplicate). Scoped by userId+tenantId rather than shared guard filter. | No transport to physical agents beyond DB polling (by design). No WebSocket push of commands. | Medium | Fully functional pull-based edge mgmt. Dual-auth (JWT for operators, edgeToken for agents). No stubs.
Floor-plans | Complete | 90 | Full CRUD, DWG/DXF upload to local disk, async parse pipeline, robust DWGParserService (dxf-parser + libredwg/ODA/WSL fallbacks, AIA layer classification, wall-merge, room detection, canvas PNG thumbnail), 3D device add/position/animation, zones, building 3D metadata, statistics, 3D simulation data. Has spec test. | File storage local disk only (not S3). DWG→DXF depends on external binaries. Service scopes only by userId (no tenantId). | No cloud/persistent object storage; uploaded files on ephemeral container FS. | Low | Surprisingly complete; DWG parser is genuinely production-grade. Risk is FS storage + external binary dependency for .dwg.
Images | Partial | 45 | Rich image metadata entity (dimensions, thumbnails, EXIF, association, counters). CRUD DB ops work: create, findAll (paginated), findOne, soft remove, statistics. | Upload endpoint (controller L46) TODO — FileInterceptor default memory storage, no diskStorage/S3, so file.filename undefined; saves DB record pointing to /uploads/images/undefined. remove() (service L77) TODO — never deletes underlying file. | Entire physical file storage layer (S3/disk write, thumbnail gen, EXIF extraction, serving/download). isPublic/viewCount/thumbnails/entityType never populated. | Low | Metadata scaffolding only; actual image storage is a stub. Records reference non-existent files. Two confirmed TODOs.
Automation | Partial | 85 | Full CRUD with tenant/customer scoping, statistics, execution-log pagination; Kafka consumer on telemetry.device.validated runs processor; trigger evaluation (eq/ne/gt/gte/lt/lte/between, dot-notation); executeAction handles device commands via GatewayService, MQTT publish, axios webhooks; AutomationLog written on every success/failure. | executeNotification is a MOCK stub ('[MOCK] Would send notification' — NotificationService not injected). executeManually only bumps counters with a TODO. | No @Cron calls processScheduledAutomations, so 'schedule'-type triggers never auto-fire. Notification delivery absent. | High | Prior TODOs for DeviceCommand/MQTT now largely resolved (gateway+MQTT wired); only notifications + scheduled-trigger cron remain.
Rules | Complete | 88 | rule-engine.service.ts fully implemented (no longer near-empty): chain selection by messageTypes/deviceTypes, node graph traversal, 50-hop loop guard, per-node/chain stat persistence, sub-chain execution. RuleEngineConsumer subscribes to Kafka 'rules.input' genuinely produced by telemetry.consumer. Full RuleChain CRUD, activate/deactivate, statistics. | Chain execution doesn't enforce configuration.maxExecutionTime/retryOnFailure. Node stat saves fire-and-forget. | entities/rule-node.entity.ts + rule-connection.entity.ts are empty dead files (nodes/connections live in the nodes module). | High | Was the CLAUDE.md 'essentially empty' item; now the most complete part of the rule stack.
Nodes | Complete | 92 | All 8 processors implemented + wired in NodeProcessorFactory: FILTER, TRANSFORMATION, ENRICHMENT (device/customer attrs), ACTION (save_telemetry/attrs/create_alarm/send_email/rest_api_call/mqtt_publish via real repos/Mail/MQTT/axios), SWITCH, SCRIPT (vm sandbox w/ timeout), EXTERNAL, FLOW (sub-chain w/ circular detection, lazy ModuleRef). Node CRUD + stats. | EnrichmentNodeProcessor.fetchRelatedEntities returns {} (graph traversal not implemented). FILTER + TRANSFORMATION still use unsandboxed new Function() (only SCRIPT node uses vm). | Nothing structural. | High | Most mature module in the audit; the rule engine depends entirely on it.
Scripts | Stub | 50 | Standalone script CRUD scoped by userId, line counting, statistics-by-type, soft delete. | — | test() and execute() are stubs with 'TODO: Implement actual script execution' returning mock/echo — no sandbox execution. create() never sets tenantId which entity declares non-nullable (likely insert failure). | Medium | Real sandboxed JS execution already exists in nodes/processors/script-node.ts; this module duplicates the concept but never wired it in.
Schedules | Partial | 80 | Full CRUD, per-type config validator, cron-parser nextRun, live CronJob runner (register/reschedule/unregister, reload on boot), ScheduleExecutorService writes execution logs with timing/status, history + statistics, manual execute. | Executor dispatch handlers (REPORT/BACKUP/CLEANUP/EXPORT/DEVICE_COMMAND) only emit EventEmitter events and report success immediately — they don't perform the work. | NO @OnEvent listeners for any schedule.*.requested event (verified by grep) → no reports, no backups, DEVICE_COMMAND schedules never reach a device. | Medium | Framework production-grade; the missing piece is the event consumers that do the actual tasks.
Integrations | Partial | 55 | Integration config CRUD scoped by userId, enable/disable, statistics-by-type/message-totals, derived recent-activity feed (synthesized from entity state), incrementMessageCount, rich entity with success/failure/rate-limit helpers + select:false credentials. | testConnection is a stub — 'TODO: Implement actual connection testing' always returns success. | No integration runtime engine — nothing dispatches messages to configured integrations (webhook/MQTT/cloud); no outbound pipeline. create() omits tenantId (potential insert failure). | Medium | Effectively a config store with reporting UI. Overlaps with ACTION node's rest_api_call/mqtt_publish, which ARE implemented.
Alarms | Partial | 85 | Full alarm-rule CRUD, lifecycle (trigger/acknowledge/clear/resolve), 11-operator condition evaluation, batch telemetry checking, bulk ops, statistics, rich custom repository, WebSocket gateway broadcasting via EventEmitter2. Entity has lifecycle helpers + indexes. | alarms.consumer.ts (Kafka) is NOT instantiated/wired into any module — dead code using raw pg.Pool, inconsistent table names ('alarm' vs 'alarms'), unmigrated alarm_history. Escalation via in-memory setTimeout lost on restart. | SMS notification is console.log + TODO stub (Twilio/AWS SNS). Consumer's notify/clearance/escalation methods are comment-only stubs. | High | Core IoT alerting. CRUD + real-time flow (EventEmitter→gateway) solid; Kafka consumer layer unused/incomplete; SMS unimplemented.
Analytics | Complete | 85 | Extensive 1537-line service: system overview, device analytics + drill-down, dashboard analytics, data-consumption, system-performance, geo, energy, legacy telemetry/alarm/user stats, daily @Cron rollup. Controller with JSON/CSV export. Two entities; view-logging real. | Heavy heuristics/placeholders: hardcoded uptime 99.8%, storageEfficiency 87.5%, synthetic time-series fallback, Math.random() for trend/growth/locationPerformance. Storage estimated from row-count*250 bytes. | No missing methods — all endpoints return data; accuracy of several KPIs is faked rather than computed. | Medium | Functionally complete + wired; numbers partly synthetic.
Audit | Partial | 86 | AuditService with role-based access filtering, findAll with rich filters, per-module queries, statistics, recent/failed, CSV export, deleteOld. AuditEventsService wires EventEmitter handlers (user/device/alarm) to synchronous DB writes. Also used by AuditInterceptor. | audit.consumer.ts (Kafka, ~530 lines: brute-force/mass-deletion/priv-escalation detection, IP blocking, Redis stats, archival) NOT instantiated anywhere — dead code depending on unmigrated audit_logs_archive. | Event handlers for asset/dashboard/customer/settings/rule/security events declared as topics but have no EventEmitter handler. Suspicious-activity detection only in the unwired consumer. | Medium | Live audit-logging path works; advanced security-monitoring consumer is complete code never activated.
Api-monitoring | Partial | 90 | APILog entity (sanitized req/res, indexes), createLog, tenant/user log queries, 24h metrics (success/error rate, avg response, by-endpoint/method), statistics, errors, slow-requests, top-endpoints, per-minute performance, daily @Cron cleanup. Populated by LoggingInterceptor. | getHealth() returns hardcoded {database:'healthy',redis:'healthy',mqtt:'healthy'} with 'TODO: Implement actual health checks' — the only stub. | Only the real health-probe logic behind /api-monitoring/health. | Low | Solid module; overlaps with HealthModule (which implements real probes), so the stub health endpoint is low-impact.
Metrics | Complete | 90 | PrometheusModule with default metrics (smartlife_ prefix), 10 metric providers, CustomMetricsService with typed track methods (HTTP, device connections, MQTT, Kafka, telemetry), @Public /metrics endpoint. Wired to MetricsInterceptor. | metrics.provider.ts exports a near-duplicate provider array not imported by the module (dead file). CustomMetricsService injects only 6 of 10 declared metrics; db_connections/db_queries/auth_attempts/errors_total registered but never incremented. | No wrapper methods to record DB/auth/error metrics (declared-but-unused counters). | Medium | Observability works end-to-end; some declared metrics inert; redundant provider file.
Health | Complete | 95 | Terminus HealthController with 8 @Public endpoints (root, full, liveness, readiness, database, cache, messaging) composing memory/disk/db pings. Four custom indicators fully implemented: Database (SELECT 1 + pool stats), Redis (dedicated ioredis ping), Kafka (admin describeCluster), Mqtt (connect-with-timeout probe). | Minor: DiskHealthIndicator checks path '/' and MQTT default 'mqtt://emqx:1883' assume container paths/hosts. | Nothing material. | Medium | Most complete of the monitoring modules; real probes for all critical infra.
Notifications | Partial | 70 | Full CRUD with RBAC, bulk send (users/tenant/customer), scheduled-send cron (every minute), retry-failed, statistics, event listeners (device.offline/connected, alarm.triggered), custom repository. EMAIL channel works end-to-end via MailService; IN_APP marks delivered. | SMS + PUSH channels are stubs (Twilio/AWS-SNS + FCM/APNS commented out, only log '[TWILIO] Would send...'; silently succeed in dev). Webhook send has explicit TODO (logs, never POSTs). IN_APP doesn't push to WebSocket. | notifications.gateway.ts is an empty 1-line file, not referenced by the module (unwired real-time gateway). | Medium | Core pipeline + DB/API layer production-ready; 3 of 5 delivery channels (SMS, push, webhook) are non-functional stubs.
Mail | Complete | 95 | Nodemailer transporter with SMTP verify, graceful disable when unconfigured. All auth emails: invitation, verification, welcome, password-reset, 2FA code — each pulls a DB template via EmailTemplatesService with full inline HTML fallback. Wired into Auth/Notifications modules. | Sends silently return false (not throw) when SMTP not configured — callers can't distinguish 'disabled' from 'failed'. | No attachment support wired despite EmailTemplate.settings declaring it. | High | Auth flows (verification, reset, invitations, 2FA) depend on this; solid + defensive.
Email-templates | Complete | 95 | Full CRUD, findByType (active), {{variable}} rendering with missing-var warnings, getRenderedEmail with default enrichment, preview with auto-generated sample vars, placeholder validation. Rich entity (locale, translations, settings, usage tracking) + helpers. | Entity helpers (render/getLocalized/recordUsage/translations) defined but unused by service. Unique index on [tenantId,type] but service queries by type alone (ignores tenant) → multi-tenant overrides not resolved per-tenant. | Locale/translation selection not exposed via API; usage tracking never persisted. | Medium | Works end-to-end for the single system-template-per-type case MailService relies on.
Websocket | Partial | 85 | Socket.IO gateway on /ws: connection/disconnect, subscription tracking Map, device/dashboard/widget subscribe+unsubscribe (rooms), broadcast methods (deviceTelemetry, deviceStatus, alarm, dashboardUpdate, sendToUser, stats). Consumed by Dashboards/Widgets. WsJwtGuard per-message. | handleConnection does NOT authenticate on connect (no handshake JWT); client.data never populated → device:command emits undefined userId/tenantId. device:command claims to 'forward to MQTT' but calls server.emit (broadcasts to all) — a stub. No per-tenant room isolation on connect. | Actual command dispatch to devices; connection-time auth; joining user/tenant rooms. | High | Real-time telemetry broadcast path functional; control/command path + connection auth incomplete.
Dashboards | Complete | 95 | Full CRUD with role-scoped queries, find-default, per-widget add/update/remove (JSONB) with WebSocket broadcast of device-subscription changes, share/unshare, clone (deep-copy with new widget IDs), toggle-favorite, getShared, statistics, customer assign/unassign. Access control via checkAccess. | addWidget/updateWidget/removeWidget accept `any` body (no DTO validation). Statistics favorites/shared counts re-filter on a cloned QB that may already carry a customer OR-clause. | Nothing material. | Medium | Production-ready; cleanly integrated with WebsocketGateway for live widget updates.
Widgets | Complete | 95 | WidgetTypes + WidgetBundles full CRUD, clone, import/export JSON, descriptor validation (type/size/script-tag XSS check), statistics, system-widget protection. Bundle assignment with referential guard. Comprehensive 1408-line system-widgets seed defining 30+ real widgets with full HTML/CSS/scripts. | Query DTOs declare page/limit without @Type coercion (may arrive as strings). Widget descriptor typed as `any`. Bundle-widget linkage by title string rather than FK. | No confirmation the seed auto-runs at startup; no per-widget runtime execution engine (frontend renders). | Medium | Backend widget library management complete + well-populated; rendering is a frontend concern.
Sharing | Partial | 80 | Full CRUD for shares, link-token gen/access, expiry checks, view tracking, statistics, shared-with-me listing, revoke-by-resource, tenant/owner scoping, entity helpers. | EMAIL share type validated but no email ever sent (no MailService wired). trackView increments views but never sets lastViewedAt. UsageTrackingInterceptor applied but @TrackUsage decorator commented out. | Recipient-side access enforcement beyond email match; notification/email dispatch on share creation. | Low | Clean, functional. No null/NotImplemented stubs. Main gap is email delivery for email shares.
Solution-templates | Partial | 70 | CRUD with owner/isSystem permission checks, paginated filtered listing (category/search/premium), categories with counts, statistics (byCategory, popular), install-count increment, entity helpers. | install() only increments a counter and returns a fabricated success payload — 'TODO: Implement actual installation logic' (creates no devices/dashboards/rules). rateTemplate() overwrites rating directly with 'TODO: proper rating system'. | Real template provisioning engine; per-user rating tracking. Stray unused import in controller. | Low | Catalog/browsing works end-to-end; the actual value-delivering install action is a stub.
Assignments | Complete | 95 | Two-tier (customer + user) resource assignment engine: atomic transactions, permission gates (subscription feature + customer grants + user perms), quota gates (subscription ceiling + customer allocation + per-user limits), duplicate detection, cross-tenant verification, cascade unassign, atomic jsonb_set counters, resource summary. 10 junction entities. | Inline DTOs use @IsEnum with array literal (unusual). No read/list endpoints (only assign/unassign); getUserResourceSummary service method has no controller route. | Nothing material for its scope. | High | Most sophisticated module reviewed; core to multi-tenant resource governance. Well-architected.
Lib/kafka | Complete | 95 | Idempotent producer, topic auto-creation (20 topics), single + batch send with GZIP + headers, consumer group factory with autoCommit + per-message try/catch, graceful shutdown. Global module bootstraps producer + topics via useFactory. | Consumer errors swallowed (logged, not rethrown) with a note that a DLQ should be added — no dead-letter handling yet. | Dead-letter-queue pattern; manual offset control path (documented opt-in, not implemented). | High | Solid, production-grade Kafka wrapper. Core to telemetry ingestion pipeline.
Lib/mqtt | Complete | 95 | Connect/reconnect lifecycle, subscribes to 8 uplink patterns, message handling with deviceKey/devEUI extraction, device lookup (generic + LoRaWAN devEUI), last-seen/status update, StandardTelemetry builder with shape-based LoRaWAN envelope detection (base64→hex), ChirpStack pre-decoded handling, robust QoS1 publish, clean disconnect. | publish() heavily instrumented with debug logs + emoji (leftover debugging). Device last-seen update fire-and-forget (silent failures). | Nothing material. | High | Well-implemented; documented LoRaWAN shape-detection fix present. Central to device ingestion.
Lib/redis | Complete | 100 | Comprehensive ioredis wrapper: strings, hashes, sets, sorted sets, lists, key ops, scan, transactions, pub/sub with tracked connections, cache helper with fetch-fn, invalidation by pattern, rate limiting, session helpers, distributed lock (SET NX EX with retries), health/ping/info. lazyConnect + retry strategy. | None. | Nothing. | High | Fully fleshed-out utility library, no stubs. Underpins sessions, caching, rate limiting, locks.
Common/guards | Complete | 95 | All 8 global guards in documented order: throttler, JWT auth (@Public bypass), roles, tenant isolation (tenantFilter injection), customer access (customerFilter), subscription load/health/plan gate with req caching, feature-limit, permission (role∪direct perms filtered by features, intersected with customer grants), subscription-limit quota. Plus WsJwtGuard + OAuth guards. GuardsModule wires order correctly. | PermissionGuard does a full DB user-load with relations on every permission-checked request. SubscriptionGuard treats any findByTenantId error as 'no subscription'. | Nothing material. | High | Cohesive, correctly-ordered defense-in-depth guard stack. Core to multi-tenant security.
Common/decorators | Complete | 100 | Full barrel: @Public, @Roles, @CurrentUser (+ResolvedTenantId/CustomerId), @RequirePermissions, @RequireSubscription/@RequireSubscriptionLimit, @RequireFeature, @Notify, @Audit, @IsValidPhone, and composition decorators (@TenantAdminOnly, @CustomerAdminOnly, @ProtectedRoute, @SwaggerAuth). Metadata keys align with guards/interceptors. | None. | Nothing. | High | Metadata contracts consistent with consumers. Well-documented.
Common/interceptors | Complete | 90 | Transform (response wrapping), Logging (persists APILog), Metrics (Prometheus HTTP), Audit (reads @Audit metadata), Notification (reads @Notify, resolves recipients, bulk vs single, templating, async dispatch), UsageTracking (increments tenant apiCalls), Timeout. InterceptorsModule registers 5 as APP_INTERCEPTOR. | TimeoutInterceptor + TransformInterceptor NOT registered in InterceptorsModule (Transform applied in main.ts; Timeout appears unwired). NotificationInterceptor has duplicated entityId/entityName fallbacks. Stray 'test' comment in Transform. | Nothing material. | Medium | All interceptors functional; minor wiring/registration inconsistency for Timeout.
Common/filters | Complete | 90 | Two @Catch() global filters: HttpExceptionFilter (HttpException, TypeORM QueryFailedError with PG codes 23505/23503/23502 mapping, validationErrors passthrough, dev stack traces) and AllExceptionsFilter. Consistent {success:false, statusCode, error, message, timestamp, path} shape. | Two overlapping catch-all filters exist — redundant; only one should be registered. HttpExceptionFilter is the more complete one. | Nothing. | Medium | Functional + consistent. Redundancy between the two filters is the only concern.